## Guida
Project Mathematics — Part III
ImpresaNumerica · Chapter 3 — cost estimating and EVM monitoring
This file does NOT replace your Gantt chart or your Agile board: it works alongside them. The Gantt chart / scheduling tool remains the source for dates and % progress; this file turns all of that into financial figures — cost estimating during planning (§3.1-3.4) and Earned Value monitoring during execution (§3.5-3.8), with a bridge to Agile/Kanban projects (§3.9).
How the file is organized
Parametri | Overhead rates, contingency, management reserve, CPI/SPI traffic-light thresholds, Agile parameters. Set these up first.
WBS e Stima Costi | PLANNING (§3.1-3.4): break the project down into activities (WBS), estimate them with the three-point method (O/M/P) and obtain PERT, standard deviation, direct/indirect/contingency cost and the final BAC.
Monitoraggio EVM | EXECUTION (§3.5-3.8): one row per check-point (weekly/biweekly). Enter just 3 numbers (% planned from baseline, % actual progress, actual cost) and get PV, EV, CV, SV, CPI, SPI, ETC, EAC, VAC, TCPI and Burn Rate already calculated, with an automatic traffic light.
Buffer e Contingency | Tracks the consumption of the risk reserve (contingency) risk by risk, of the management reserve, and of the project time buffer (§3.2, §3.7).
Agile - Velocity | If part of the project (or all of it) is managed via Sprint/Kanban: velocity, cost per story point, Agile Earned Value and forecast (§3.9).
Dashboard | Summary KPIs and charts (PV/EV/AC S-curve, CPI/SPI trend) automatically updated from the latest check-point entered.
Glossario | Meaning of every acronym with a reference to the book section.
Color legend
INPUT cell — enter your data here (often copied from the Gantt chart / Agile tool)
CALCULATED cell — contains a formula, do not modify
Group / section header
Recommended workflow
1. PLANNING — In 'Parametri' set overhead, contingency and thresholds. In 'WBS e Stima Costi' enter the activities with the O/M/P estimates: you get the BAC (project budget).
2. KICK-OFF — Freeze the BAC as the baseline: from this point on it is the fixed reference for every future variance (§3.4).
3. EXECUTION — At each check-point (from your Gantt chart or your Agile board) record on 'Monitoraggio EVM' the % planned, the % actual and the actual cost: everything else calculates itself.
4. CONTROL — Check 'Dashboard' for the summary traffic light; if CPI or SPI fall outside the threshold, decide whether to reschedule, renegotiate or take corrective action (§3.6).
5. RESERVES — Every time you use contingency or management reserve for a specific risk, record it in 'Buffer e Contingency': they must not be consumed 'by feel'.
6. AGILE — If part of the project is run in sprints, update 'Agile - Velocity' at the end of every sprint: its EV in euros is added to that of the other workstreams in the Dashboard.

## Parametri
Project parameters
Constants shared by cost estimating, EVM monitoring and Agile (§3.2, §3.7-3.9)
Costs and reserves (§3.2)
Parameter | Value | Unit | Description
Overhead rate (indirect costs) | 10% | % | Percentage of direct costs allocated to structure/management (§2.5, §3.2)
Contingency (known-risk reserve) | 15% | % | 5% for standard projects, 20-30% for innovative/unstable projects (§3.2)
Management Reserve | 5% | % | Reserve available to the sponsor for contingencies not related to a known risk (§3.4, §3.7)
CPI / SPI traffic-light thresholds (§3.8)
Green threshold (on track) | 0.95 |  | CPI/SPI >= this value -> Healthy
Yellow threshold (caution) | 0.85 |  | CPI/SPI between this value and the green threshold -> Caution; below -> Critical
Project (§3.4)
Project start date | 2027-01-01 |  | Baseline start date
Planned project end date | 2027-04-30 |  | Baseline end date (used to calculate % time elapsed)
Initial project buffer (Critical Chain) | 10 | days | Aggregated buffer protecting the project end date (§3.7)
Agile / Flow parameters (§3.9)
Sprint duration | 14 | days | Standard length of a sprint
Team cost per sprint (fully loaded) | 12000 | € | Fully loaded cost of the Agile team per sprint (Chap. 2, §2.2-2.5)
No. of sprints for the velocity moving average | 4 |  | Typically 3-6 sprints (§3.9.3)

## WBS e Stima Costi
WBS and Cost Estimate — planning (§3.1-3.4)
ID | Attivita | Fase | Risorsa | CostoOrario | O | M | P | PERT | Sigma | OreGiorno | EffortOre | CostoPersone | Materiali | ServiziEsterni | CostoDiretto | CostoIndiretto | CostoAttivita | DataInizio | DurataGg | DataFine | PesoPct
1.1 | C451 | Execution | Worker | 71.625 | 8 | 11 | 13 | 10.8333 | 0.83333 | 8 | 86.6667 | 6207.5 | 0 | 0 | 6207.5 | 620.75 | 6828.25 | 2026-01-01 | 10.8333 | 2026-01-11 20:00 | 14.04%
1.2 | C462 | Execution | Worker | 71.625 | 8 | 11 | 13 | 10.8333 | 0.83333 | 8 | 86.6667 | 6207.5 | 0 | 0 | 6207.5 | 620.75 | 6828.25 | 2026-01-01 | 10.8333 | 2026-01-11 20:00 | 14.04%
1.3 | C463 | Execution | Worker | 71.625 | 8 | 11 | 13 | 10.8333 | 0.83333 | 8 | 86.6667 | 6207.5 | 0 | 0 | 6207.5 | 620.75 | 6828.25 | 2026-01-15 | 10.8333 | 2026-01-25 20:00 | 14.04%
1.4 | C464 | Execution | Worker | 71.625 | 8 | 11 | 13 | 10.8333 | 0.83333 | 8 | 86.6667 | 6207.5 | 0 | 0 | 6207.5 | 620.75 | 6828.25 | 2026-01-15 | 10.8333 | 2026-01-25 20:00 | 14.04%
1.5 | C465 | Execution | Worker | 71.625 | 8 | 11 | 13 | 10.8333 | 0.83333 | 8 | 86.6667 | 6207.5 | 0 | 0 | 6207.5 | 620.75 | 6828.25 | 2026-01-27 | 10.8333 | 2026-02-06 20:00 | 14.04%
1.6 | C471 | Execution | Worker | 71.625 | 4 | 5 | 6 | 5 | 0.33333 | 8 | 40 | 2865 | 0 | 0 | 2865 | 286.5 | 3151.5 | 2026-01-27 | 5 | 2026-02-01 | 6.479%
1.7 | C951 | Execution | Worker | 71.625 | 4 | 5 | 6 | 5 | 0.33333 | 8 | 40 | 2865 | 0 | 0 | 2865 | 286.5 | 3151.5 | 2026-02-10 | 5 | 2026-02-15 | 6.479%
1.8 | C952 | Execution | Worker | 71.625 | 5 | 7 | 9 | 7 | 0.66667 | 8 | 56 | 4011 | 0 | 0 | 4011 | 401.1 | 4412.1 | 2026-02-05 | 7 | 2026-02-12 | 9.071%
1.9 | C953 | Execution | Worker | 71.625 | 5 | 6 | 7 | 6 | 0.33333 | 8 | 48 | 3438 | 0 | 0 | 3438 | 343.8 | 3781.8 | 2026-02-20 | 6 | 2026-02-26 | 7.775%
Project summary — from WBS to Budget At Completion (BAC)
Total effort (person-days, sum of PERT) | 77.1667
Project standard deviation (σ, independent activities) | 2.0616
Total labor cost | 44216.5
Total direct cost | 44216.5
Total indirect cost (overhead) | 4421.65
Subtotal (direct + indirect) | 48638.15
Contingency (known-risk reserve) | 7295.7225
BAC — Budget At Completion | 55933.8725
Management Reserve (extra, available to the sponsor) | 2796.6936
Total approved budget (BAC + Management Reserve) | 58730.5661
Average cost per person-day | 573
Estimated cost range (±1σ, approximate) | ± 1,181 € (68% probability) on a BAC of 55,934 €
Formulas:
DataFine = IF([ID]="","",[DataInizio]+[DurataGg])
Note on B25: σ_progetto = radice quadrata della somma dei quadrati delle σ di attività (§3.3)
Note on B30: Da tracciare rischio per rischio nel foglio 'Buffer e Contingency' (§3.2)

## Monitoraggio EVM
Monitoraggio EVM — execution (§3.5-3.8)
Data | Nota | PctPianificato | PV | PctReale | EV | AC | CV | SV | CPI | SPI | Stato | ETC | EAC | EACott | EAClin | VAC | TCPI | ACperiodo | PVperiodo | BurnRate | PctTempo
2026-01-01 | Start of Work | 0% | 0 | 0% | 0 | 2000 | -2000 | 0 | 0 |  |  |  | #VALUE! | 57933.8725 |  | #VALUE! | 1.0371 | 2000 | 0 |  | -306.7%

## Buffer e Contingency
Buffer e Contingency — reserves tracked risk by risk
Contingency — known-risk reserve, tracked risk by risk (§3.2)
Rischio | Probabilita | ImpattoStimato | ContingenzaStanziata | DataUtilizzo | ImportoUtilizzato | Residuo | Stato
Equipment Delivery Delay | 40% | 8000 | 15000 |  | 0 | 15000 | Not triggered
Total contingency allocated (from risks) | 15000
Total used | 0
Contingency at budget (from WBS) | 7295.7225
Management Reserve — sponsor reserve for contingencies not related to a known risk (§3.4, §3.7)
Data | Descrizione | ApprovatoDa | Importo | Note
Management Reserve at budget (from WBS) | 2796.6936
Total used | 0
Remaining | 2796.6936
Project time buffer — Critical Chain (§3.7)
Initial buffer | 10
Buffer consumed to date | 0
% Buffer consumed | 0%
% Project completed (latest data from Monitoraggio EVM) | 0%
Buffer health index (%consumed / %completed)
Note on B16: Confronto con la contingency calcolata nel foglio WBS: se molto diversa, aggiorna l'elenco rischi
Note on B33: Giorni di buffer già utilizzati per assorbire ritardi (dal tuo Gantt/Critical Chain)
Note on B36: < 1 = il buffer si consuma più lentamente dell'avanzamento (sano). > 1 = allarme anticipato: il progetto consuma riserva più velocemente di quanto avanzi (§3.7)

## Agile - Velocity
Agile / Flow — Velocity and generalized Earned Value (§3.9)
Sprint tracker
Sprint | DataInizio | DataFine | SPPianificati | SPCompletati | Velocity | VelocityMedia | CostoTeamSprint | CostoPerSP | SPCumulati | EVAgile | ACCumulato | CPIAgile | BacklogResiduo | SprintResidui | EACtempoGg | EACcosto
Sprint 1 |  |  | 30 | 24 | 24 | 24 | 12000 | 500 | 24 | 12000 | 12000 | 1 | 180 | 7.5 | 105 | 102000
Sprint 2 |  |  | 30 | 28 | 28 | 26 | 12000 | 461.5385 | 52 | 24000 | 24000 | 1 | 152 | 5.8462 | 81.8462 | 94153.8462
Sprint 3 |  |  | 30 | 31 | 31 | 27.6667 | 12000 | 433.7349 | 83 | 36000 | 36000 | 1 | 121 | 4.3735 | 61.2289 | 88481.9277
Flow — Kanban and Little's Law (§3.9.5)
Throughput (items completed/week) | 8
Average Cycle Time (days) | 6
Theoretical WIP (Little's Law: Throughput x Cycle Time / 7 days) | 6.8571
Observed WIP (items actually in progress) | 6
Variance (Observed WIP - Theoretical WIP) | -0.85714
Note on B25: WIP = Throughput x Cycle Time (§3.9.5); Throughput settimanale convertito in coerenza con Cycle Time in giorni
Note on B27: Positivo e crescente: troppo lavoro aperto in parallelo rispetto alla capacita reale del team (§3.9.5)

## Dashboard
Project dashboard
Latest check-point available from 'Monitoraggio EVM' (§3.5-3.8)
Summary KPIs (latest check-point)
BAC — Budget At Completion | 55933.8725
PV — Planned Value | 0
EV — Earned Value | 0
AC — Actual Cost | 2000
CPI — Cost Performance Index | 0
SPI — Schedule Performance Index
Project status
EAC — Estimate At Completion
VAC — Variance At Completion
TCPI — efficiency required from here to completion | 1.0371
% Actual progress | 0%
% Time elapsed | -306.7%
Hybrid program view — sum of the Gantt/EVM and Agile workstreams (§3.9.4)
Program EV (Gantt/EVM EV + Agile EV) | 36000
Program AC (Gantt/EVM AC + Agile AC) | 38000
Program CPI | 0.94737
Charts
Note on B19: EV_programma = somma degli EV dei singoli filoni, indipendentemente dal metodo di misura nativo (§3.9.4)

## Glossario
Glossary
Meaning of every acronym used in the file, with a reference to the book section (Part III, Chap. 3)
Acronym | Meaning / formula | Ref.
O / M / P | Optimistic / Most likely / Pessimistic estimate (three-point) | §3.3
PERT | Weighted estimate = (O + 4M + P) / 6 | §3.3
Sigma (σ) | Standard deviation of the estimate = (P - O) / 6 | §3.3
BAC | Budget At Completion — total budget approved at baseline | §3.4
Contingency | Reserve for known and assessed risks, tracked risk by risk | §3.2
Management Reserve | Reserve available to the sponsor for contingencies not related to a known risk | §3.4, §3.7
PV | Planned Value — value that should have been completed by date T, per baseline | §3.5
AC | Actual Cost — cost actually incurred by date T | §3.5
EV | Earned Value — value of the work actually completed by date T = %actual x BAC | §3.5
CV | Cost Variance = EV - AC (negative = spending more than the value produced) | §3.6
SV | Schedule Variance = EV - PV (negative = behind schedule) | §3.6
CPI | Cost Performance Index = EV / AC (1 = on track, <1 = inefficient) | §3.8
SPI | Schedule Performance Index = EV / PV (1 = on track, <1 = behind schedule) | §3.8
ETC | Estimate To Complete = (BAC - EV) / CPI — estimated remaining cost | §3.6
EAC | Estimate At Completion = AC + ETC — projected final cost | §3.6
VAC | Variance At Completion = BAC - EAC — expected final variance | §3.6
TCPI | To-Complete Performance Index = (BAC - EV) / (BAC - AC) — efficiency required from here to completion | §3.6, §3.8
Burn Rate | Period AC / Period PV — rate of cash consumption vs. plan | §3.8
Forecast Accuracy | 1 - ¦EAC - Actual final cost¦ / Actual final cost (only at closeout) | §3.8
Project buffer | Aggregated time margin protecting the critical milestones (Critical Chain) | §3.7
SP (Story Point) | Relative measure of the complexity/effort of a user story | §3.9.3
Velocity | Sum of the SP completed (Definition of Done) in a sprint | §3.9.3
Average velocity | Moving average of velocity over the last N iterations (typically 3-6) | §3.9.3
Cost per SP | Fully loaded team cost per sprint / Average velocity | §3.9.4
Agile EV | Cumulative SP completed x Cost per SP — generalized Earned Value | §3.9.4
Throughput | Number of items completed per unit of time (items/week) | §3.9.5
Cycle Time | Time from the actual start of work to completion | §3.9.5
WIP | Work In Progress = Throughput x Cycle Time (Little's Law) | §3.9.5
Scope buffer | Low-priority backlog items, the first to be cut if velocity drops | §3.9.7
WIP limit | Explicit limit on the number of items that can be worked on in parallel | §3.9.7